## Cover
Scrum Reporting Form
| Day | 2023-04-19
| Due Date | 2023-04-20
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
You have had an opportunity to decide on a project and start the general set-up for the project. The next step is to go through and identify all the tasks that need to be commpleted to have a finished product for the Final Project Presentation. The Fibonacci Sequence to assign importance of each task. Rate the tasks by the importance of when they need to be done as well as the importance to the completion of the project. Some tasks with a low priority may never be completed. Those can be saved for a later project. Come back to this list each day, mark tasks that have been completed as "Done" and repriotize the remaining tasks.
| Plans for | 2023-04-20
| Team Member | Tasks planned | Prriority
| All | Decide on Project | 1
| All | Identify major parts of the project | 2
| All | Set up GitHub account and invite all participants | 3
| Isaiah | Work on randomization algorithm and check | 4
| Carter | Work on Board and make sure Board is printing correctly | 5
| Hosea | Research coordinate systems for 2d arrays | 6
| All | Break up project into modules (use UML diagrams) | 7
| Story behind your project | We decided to recreate the game, sudoku. Sudoku is a game played with numbers on a 9 x 9 grid. Each row and column must have numbers 1 through 9, used only once. There are also smaller squares made on a 3 x 3 grid. Each square must also have numbers 1 through 9. There must be no repeats and intersection in a row, column, or square. First, a board is printed a 9x9 the whole board is made and certain parts are hidden. Each board is randomized but has to follow the rules of sudoku. The most difficult part of the project is creating a check to make sure that each row, column, and square is having random numbers which have numbers 1 thorugh 9. An interesting part of the project is user interaction is making it into a grid and coordinate system. This makes the user select what want coordinate they want then input it. After seeing if their input is equal to the answer. If it is correct then the number would become visible. If it is not correct they would get to try again.

## 20 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-20 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-21
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-20 | Prriority
| Team Member | Tasks planned
| All | Decide on Project | 1
| All | Identify major parts of the project | 2
| All | Set up GitHub account and invite all participants | 3
| Isaiah | Work on randomization algorithm and check | 4
| Carter | Work on Board and make sure Board is printing correctly | 5
| Hosea | Research coordinate systems for 2d arrays | 6
| All | Break up project into modules (use UML diagrams) | 7
| Plans for | 2023-04-21
| Team Member | Tasks planned
| Carter/Isaiah | Incorporate algorithm with the Board | 1
| Hosea | Start implementing a coordinate system | 2
| TBA | To Be Determined | ?
| TBA | To Be Determined | ?

## 21 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-20 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-23
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-20 | Prriority
| Team Member | Tasks planned
| Carter/Isaiah | Incorporate algorithm with the Board | 1
| Hosea | Start implementing a coordinate system | 2
| TBA | To Be Determined | ?
| TBA | To Be Determined | ?
| Plans for | 2023-04-23
| Team Member | Tasks planned
| TBA | To Be Determined | ?

## 24 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-23 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-24
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-23 | Prriority
| Team Member | Tasks planned
| TBA | To Be Determined | ?
| 0 | 0 | 0
| 0 | 0 | 0
| Plans for | 2023-04-24
| Team Member | Tasks planned
| TBA | To Be Determined | ?

## 25 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-24 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-25
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-24 | Prriority
| Team Member | Tasks planned
| TBA | To Be Determined | ?
| 0 | 0 | 0
| 0 | 0 | 0
| Plans for | 2023-04-25
| Team Member | Tasks planned

## 26 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-25 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-26
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-25 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-04-26
| Team Member | Tasks planned

## 27 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-26 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-27
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-26 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-04-27
| Team Member | Tasks planned for Project Presentration

## 28 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-27 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-30
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-27 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-04-30
| Team Member | Tasks planned for Project Presentration

## 1 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-30 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-01
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-30 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-01
| Team Member | Tasks planned for Project Presentration

## 2 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-01 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-02
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-05-01 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-02
| Team Member | Tasks planned for Project Presentration

## 3 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-02 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-03
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-05-02 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-03
| Team Member | Tasks planned for Project Presentration

## 4 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-03 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-04
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-05-03 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-04
| Team Member | Tasks planned for Project Presentration

## 5 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-04 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-07
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-05-04 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-07
| Team Member | Tasks planned for Project Presentration

## Final
Scrum Reporting Form |  |  | Priority | Status | Final Thoughts on this Process
| Day | 2023-05-07 |  | Either DONE or what problem needs to be solved before the task can be completed. | This page is the last Scrum Form due and is to record your final thoughts on the process
| Due Day | Today
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall
| Board.h | Carter McCall
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-05-07
| Team Member | Presentaion | Prriority
|  | Present slide show and program deminstration | 1
Isaiah
| Plans for | Today
| Team Member | Tasks planned
None - complete