## Cover
Scrum Reporting Form
| Day | 2023-04-19
| Due Date | 2023-04-20
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
You have had an opportunity to decide on a project and start the general set-up for the project. The next step is to go through and identify all the tasks that need to be commpleted to have a finished product for the Final Project Presentation. The Fibonacci Sequence to assign importance of each task. Rate the tasks by the importance of when they need to be done as well as the importance to the completion of the project. Some tasks with a low priority may never be completed. Those can be saved for a later project. Come back to this list each day, mark tasks that have been completed as "Done" and repriotize the remaining tasks.
| Plans for | 2023-04-20
| Team Member | Tasks planned | Prriority
| All | Decide on Project | 1 | DONE, decided to make a sudoku game
| All | Identify major parts of the project | 2 | DONE, make a board, algorithm for checks, and a coordinate system to access board
| All | Set up GitHub account and invite all participants | 3 | DONE, Carter made a GitHub, which was accessed by Isaiah and Hosea
| Isaiah | Work on randomization algorithm and check | 4 | TO DO, randomize board correctly
| Carter | Work on Board and make sure Board is printing correctly | 5 | TO DO, use a 2d array to print out a 9x9 grid of numbers and another grid of letters and numbers above it
| Hosea | Research coordinate systems for 2d arrays | 6 | TO DO, look at websites and figure out what needs to be done
| All | Break up project into modules (use UML diagrams) | 7 | DONE, made separate modules for different parts of the program
| Story behind your project | We decided to recreate the game, sudoku. Sudoku is a game played with numbers on a 9 x 9 grid. Each row and column must have numbers 1 through 9, used only once. There are also smaller squares made on a 3 x 3 grid. Each square must also have numbers 1 through 9. There must be no repeats and intersection in a row, column, or square. First, a board is printed a 9x9 the whole board is made and certain parts are hidden. Each board is randomized but has to follow the rules of sudoku. The most difficult part of the project is creating a check to make sure that each row, column, and square is having random numbers which have numbers 1 thorugh 9. An interesting part of the project is user interaction is making it into a grid and coordinate system. This makes the user select what want coordinate they want then input it. After seeing if their input is equal to the answer. If it is correct then the number would become visible. If it is not correct they would get to try again.

## 20 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-20 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-21
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-20 | Prriority
| Team Member | Tasks planned
| All | Decide on Project | 1 | DONE, decided to make a sudoku game
| All | Identify major parts of the project | 2 | DONE, make a board, algorithm for checks, and a coordinate system to access board
| All | Set up GitHub account and invite all participants | 3 | DONE, Carter made a GitHub, which was accessed by Isaiah and Hosea
| Isaiah | Work on randomization algorithm and check | 4 | DOING, can randomize board correctly, however, can only print 3 squares correctly so need more time to add all 9 squares
| Carter | Work on Board and make sure Board is printing correctly | 5 | DOING, printing multiple areas of the array multiple times, need to add a check using if statements
| Hosea | Research coordinate systems for 2d arrays | 6 | DOING, looking at websites and asking questions
| All | Break up project into modules (use UML diagrams) | 7 | DONE, made separate modules for different parts of the program
| Plans for | 2023-04-21
| Team Member | Tasks planned
| Carter/Isaiah | Incorporate algorithm with the Board | 1 | DOING, needs to have a full board printing and then checks to make sure Board is printing
| Hosea | Start implementing a coordinate system | 2 | TO DO, needs to access the 2d array in order to have a x and y c oordinate be interactable

## 21 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-20 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-23
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-20 | Prriority
| Team Member | Tasks planned
| Carter/Isaiah | Incorporate algorithm with the Board | 1 | DOING, needs to have a full board printing and then checks to make sure Board is printing
| Hosea | Start implementing a coordinate system | 2 | TO DO, needs to access the 2d array in order to have a x and y c oordinate be interactable
| Plans for | 2023-04-23
| Team Member | Tasks planned
| N/A | Nothing Planned | N/A | N/A

## 24 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-23 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-24
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-23 | Prriority
| Team Member | Tasks planned
| N/A | Nothing Planned | N/A | N/A
| Plans for | 2023-04-24
| Team Member | Tasks planned
| Isaiah | Algorithim | 1 | DOING, continue using brute force to correct issues within the algorithm, through a series of checks
| Carter | Board printing | 2 | TO DO, implement the if statement to check numbers in the 2d array
| Hosea/Carter | Accessing 2d array and coordinate system | 3 | TO DO, Add a 1d array of strings for letters and a variable for numbers

## 25 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-24 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-25
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-24 | Prriority
| Team Member | Tasks planned
| Isaiah | Algorithim | 1 | DOING, continue using brute force to correct issues within the algorithm, through a series of checks
| Carter | Board printing | 2 | DONE, implemented the if statement to check numbers in the 2d array
| Hosea/Carter | Accessing 2d array and coordinate system | 3 | DONE, Added a 1d array of strings for letters and a variable for numbers
| Plans for | 2023-04-25
| Team Member | Tasks planned
| Isaiah | Finish Algorithm | 1 | ON HOLD, Isaiah is currently not avalible
| Carter | Incorporate Algorithm | 2 | TO DO, add Alg.cpp and Alg.h to program from Git Hub
| Hosea | Reformat and add coments | 3 | TO DO, add comments to make program more understandable and team friendly

## 26 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-25 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-26
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-25 | Prriority
| Team Member | Tasks planned
| Isaiah | Finish Algorithm | 1 | ON HOLD, Isaiah is currently not avalible
| Carter | Incorporate Algorithm | 2 | DONE, added Alg.cpp and Alg.h to program from Git Hub
| Hosea | Coordinate System | 3 | DONE, added comments to make program more understandable and team friendly
| Plans for | 2023-04-26
| Team Member | Tasks planned
| Isaiah | Finish Algorithm | 1 | ON HOLD, Isaiah is currently not avalible
| Carter | Start Presentatation | 2 | TO DO, start presentation while waiting for Isaiah to comeback

## 27 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-26 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-27
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-26 | Prriority
| Team Member | Tasks planned
| Isaiah | Finish Algorithm | 1 | ON HOLD, Isaiah is currently not avalible
| Carter | Start Presentatation | 2 | DOING, started presentation while waiting for Isaiah to comeback
| Plans for | 2023-04-27
| Team Member | Tasks planned for Project Presentration
| Isaiah | Finish Algorithm | 1 | ON HOLD, Isaiah is currently not avalible
| Carter/ Hosea | Start Presentatation | 2 | DOING, started presentation while waiting for Isaiah to comeback

## 28 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-27 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-30
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-27 | Prriority
| Team Member | Tasks planned
| Isaiah | Finish Algorithm | 1 | ON HOLD, Isaiah is currently not avalible
| Carter/ Hosea | Start Presentatation | 2 | DOING, started presentation while waiting for Isaiah to comeback
| Plans for | 2023-04-30
| Team Member | Tasks planned for Project Presentration
| N/A | Nothing Planned | N/A | N/A

## 1 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-30 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-01
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-04-30 | Prriority
| Team Member | Tasks planned
| N/A | Nothing Planned | N/A | N/A
| Plans for | 2023-05-01
| Team Member | Tasks planned for Project Presentration
| Isaiah | Finish Algorithm | 1 | DOING, check works however, randomization does not work
| Carter | Add a way to access specific integers | 2 | TO DO, use to integers to return another at a specific area
| Isaiah | Randomization | 3 | TO DO, make randomziation for board
| Carter/Hosea | Add game play loop | 4 | TO DO, add a gameplay loop so the user is prompted more than once
| All | Presentation | 5 | DOING, started presentation

## 2 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-01 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-02
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-05-01 | Prriority
| Team Member | Tasks planned
| Isaiah | Finish Algorithm | 1 | DONE, check works however, randomization does not work
| Carter | Add a way to access specific integers | 2 | DONE, used to integers to return another at a specific area
| Isaiah | Randomization | 3 | DOING, make randomziation for board
| Carter/Hosea | Add game play loop | 4 | TO DO, add a gameplay loop so the user is prompted more than once
| All | Presentation | 5 | DOING, started presentation
| Plans for | 2023-05-02
| Team Member | Tasks planned for Project Presentration
| Isaiah | Randomization | 1 | DOING, make randomziation for board
| Carter/Hosea | Add game play loop | 2 | TO DO, add a gameplay loop so the user is prompted more than once
| All | Presentation | 3 | DOING, started presentation

## 3 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-02 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-03
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-05-02 | Prriority
| Team Member | Tasks planned
| Isaiah | Randomization | 1 | DOING, very complex issues, the vectors are not working, and not efficent
| Carter/Hosea | Add game play loop | 2 | DOING, adding a gameplay loop so the user is prompted more than once
| Hosea | Make boards using 2d arrays | 3 | DOING, started making boards
| All | Presentation | 4 | DOING, started presentation
| Plans for | 2023-05-03
| Team Member | Tasks planned for Project Presentration
| Isaiah | Work on check and improvement | 1 | DOING, improving the current check and making it compatible with Board.cpp
| Carter/Hosea | Add game play loop | 2 | DOING, adding a gameplay loop so the user is prompted more than once
| Hosea | Make boards using 2d arrays | 3 | DONE, completed making boards
| All | Presentation | 4 | DOING, started presentation

## 4 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-03 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-04
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-05-03 | Prriority
| Team Member | Tasks planned
| Isaiah | Work on check and improvement | 1 | DONE, the check works and is compatible with Board.cpp
| Carter/Hosea | Add game play loop | 2 | DOING, adding a gameplay loop so the user is prompted more than once
| Isaiah | Start Randomization using different method | 3 | DOING, reasearch based on randomizing specific rows, checking for exceptions
| All | Presentation | 4 | DOING, started presentation
| Plans for | 2023-05-04
| Team Member | Tasks planned for Project Presentration
| Isaiah | Start Randomization using different method | 1 | DOING, reasearch based on randomizing specific rows, checking for exceptions
| Carter/Hosea | Add game play loop | 2 | DOING, adding a gameplay loop so the user is prompted more than once
| All | Presentation | 3 | DOING, started presentation

## 5 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-04 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-07
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-05-04 | Prriority
| Team Member | Tasks planned
| Isaiah | Start Randomization using different method | 1 | DOING, reasearch based on randomizing specific rows, checking for exceptions
| Carter/Hosea | Add game play loop | 2 | DOING, adding a gameplay loop so the user is prompted more than once
| All | Presentation | 3 | DOING, started presentation
| Plans for | 2023-05-07
| Team Member | Tasks planned for Project Presentration

## Final
Scrum Reporting Form |  |  | Priority | Status | Final Thoughts on this Process
| Day | 2023-05-07 |  | Either DONE or what problem needs to be solved before the task can be completed. | This page is the last Scrum Form due and is to record your final thoughts on the process
| Due Day | Today
| Team Name: | Low Expectations
| Team Members: | Carter McCall, Hosea Masih, Isaiah Hocking
| Project: | Sudoku Puzzle
Division of Labor
| Module Name | Author
| Main.cpp | All
| Board.cpp | Carter McCall & Hosea Masih
| Board.h | Carter McCall & Hosea Masih
| Coord.cpp | Hosea Masih
| Coord.h | Hosea Masih
| Alg.cpp | Isaiah Hocking
| Alg.h | Isaiah Hocking
| Tasks Due | 2023-05-07
| Team Member | Presentaion | Prriority
|  | Present slide show and program deminstration | 1
Isaiah
| Plans for | Today
| Team Member | Tasks planned
None - complete